## Project Cost
PROJECT TITLE | Computer Vision Image Similarity Search for Trademark
PROJECT MANAGER | Krishnar Ram A/L Murugan (B031910013)
GROUP MEMBER NAME | Yoong Cheng Nee (B031910119), Ding Xue Wing (B031910353)
GROUP NAME | Realify
COMPANY NAME | Realify Sdn. Bhd.
DATE | 2021-11-08
GITHUB
Project Cost Estimation
| #Units/Hrs | Cost/Unit/Hr | Subtotals | WBS Level 1 Totals | % of total
WBS Items
1. Project Management |  |  |  | 290200 | 24.1302
Project Manager | 960 | 100 | 96000
Project team members | 1920 | 75 | 144000
Contracters (10% of software development and testing) |  |  | 50200
2. Hardware |  |  |  | 46000 | 3.8249
2.1 Handheld devices | 50 | 600 | 30000
2.2 Servers | 4 | 4000 | 16000
3. Software |  |  |  | 463000 | 38.4986
3.1 Licensed software | 100 | 200 | 20000
3.2 Software development* |  |  | 443000
4. Testing (10% of total hardware and software costs) |  |  | 59000 | 59000 | 4.9059
5. Training and Support |  |  |  | 144000 | 11.9737
Project team members | 1920 | 75 | 144000
6. Reserves (20% of total estimate) |  |  | 200440 | 200440 | 16.6667
Total project cost estimate |  |  |  | 1202640
* See software development estimate

## Software Cost
PROJECT TITLE | Computer Vision Image Similarity Search for Trademark
PROJECT MANAGER | Krishnar Ram A/L Murugan (B031910013)
GROUP MEMBER NAME | Yoong Cheng Nee (B031910119), Ding Xue Wing (B031910353)
GROUP NAME | Realify
COMPANY NAME | Realify Sdn. Bhd.
DATE | 2021-11-08
GITHUB
Software Development Estimation
1. Labour Estimate | #Units/Hrs | Cost/Unit/Hr. | Subtotals | Calculations
Project team member estimate | 1920 | 75 | 144000 | 1920*75
Contractor labour estimate | 2990 | 100 | 299000 | 3000*150
Total Labour Estimate |  |  | 443000 | Sum of above value
2. Function Point Estimate | Quantity | Conversion Factor | Function Point | Calculations
External Input | 10 | 4 | 40 | 10*4
External Interface files | 5 | 10 | 50 | 5*10
External outputs | 5 | 5 | 25 | 5*5
External queries | 7 | 4 | 28 | 7*4
Logical Internal tables | 6 | 7 | 42 | 6*7
Total function points |  |  | 185 | Sum of above function point values
Python language equivalency value |  |  | 55 | Assumed value from reference
Source lines of code estimate |  |  | 13500
Productivity*KSLOC^Penalty |  |  | 30.22 | Assumed value
Total labour hours (182 hours/month) |  |  | 5500.04 | 30.22*182
Cost/labour hour (RM100/hour) |  |  | 100 | Assumed value from budget expert
Total Function point estimate |  |  | 550004 | 5500.04*100