## Time management Gantt chart
PROJECT TITLE | Computer Vision Image Similarity Search for Trademark
PROJECT MANAGER | Krishnar Ram A/L Murugan (B031910013)
GROUP MEMBER NAME | Yoong Cheng Nee (B031910119), Ding Xue Wing (B031910353)
GROUP NAME | Realify
COMPANY NAME | Realify Sdn. Bhd.
DATE | 2021-10-25
GITHUB | https://github.com/krishnainc/Realify.git
[ Project Name ]
| TASK NAME | START DATE | END DATE | DURATION (days)
| Planning | 2021-10-15 | 2021-10-22 | 8
| Wireframes | 2021-10-22 | 2021-10-23 | 2
| Image Sourcing | 2021-10-22 | 2021-10-25 | 4
| Graphics | 2021-10-26 | 2021-10-31 | 6
| Design | 2021-11-01 | 2021-11-05 | 5
| Search Incorporation | 2021-11-06 | 2021-11-10 | 5
| Control Scope | 2021-11-08 | 2021-11-11 | 4
| Monitoring | 2021-11-11 | 2021-11-18 | 8
| Testing | 2021-11-19 | 2021-11-23 | 5
| Optimization | 2021-11-20 | 2021-11-25 | 6
| Platform Adaptation | 2021-11-26 | 2021-12-01 | 6
| App Development | 2021-12-02 | 2021-12-10 | 9
| Marketing | 2021-12-11 | 2021-12-18 | 8
| Deliverables Verification | 2021-12-19 | 2021-12-22 | 4
| Effort & Cost Tracking | 2021-12-23 | 2021-12-29 | 7
| Performance | 2021-12-29 | 2022-01-01 | 4
| Rollout | 2022-01-01 | 2022-01-05 | 5
| Installation | 2022-01-03 | 2022-01-05 | 3
| Documentation | 2022-01-03 | 2022-01-10 | 8
| Maintenance | 2022-01-06 | 2022-01-12 | 7
MILESTONE 1:
15/10/2021
Planning
MILESTONE 2:
1/11/2021
Execution
MILESTONE 3:
21/11/2021
Monitoring
MILESTONE 5:
1/1/2022
Closure
MILESTONE 4:
29/12/2021
Performance
Right click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.