## WBS Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | Computer Vision Image similarity search for Trademark
PROJECT MANAGER | Krishnar Ram A/L Murugan
GROUP MEMBER NAME | Yoong Cheng Nee (B031910119), Ding Xue Wing (B031910353)
GROUP NAME | Realify
COMPANY NAME | Realify Sdn. Bhd.
DATE | 2021-11-02
GITHUB | [6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Project Conception & Initiation
1.1 | Project Charter | Krishnar | 2021-10-04 | 2021-10-06 | 2 | 100%
1.1.1 | Project Charter Revisions | Yoong | 2021-10-06 | 2021-10-07 | 1 | 100%
1.2 | Research | Krishnar | 2021-10-06 | 2021-10-11 | 5 | 100%
1.3 | Projections | Ding | 2021-10-07 | 2021-10-12 | 5 | 80%
1.4 | Stakeholders | Yoong | 2021-10-08 | 2021-10-12 | 4 | 85%
1.5 | Guidelines | Ding | 2021-10-09 | 2021-10-12 | 3 | 80%
1.6 | Project Initiation | Krishnar | 2021-10-13 | 2021-10-14 | 1 | 70%
2 | Project Definition & Planning
2.1 | Scope & Goal Setting | Ding | 2021-10-15 | 2021-10-18 | 3 | 60%
2.2 | Collect Requirements | Krishnar | 2021-10-18 | 2021-10-22 | 4 | 40%
2.3 | Verify Scope | Yoong | 2021-10-21 | 2021-10-25 | 4 | 60%
2.4 | Communication Plan | Krishnar | 2021-10-26 | 2021-11-01 | 6 | 70%
2.5 | Create WBS | Yoong | 2021-11-01 | 2021-11-03 | 2 | 30%
2.6 | Control Scope | Ding | 2021-11-02 | 2021-11-08 | 6 | 10%
3 | Project Launch & Execution
3.1 | Status & Tracking | Yoong | 2021-11-09 | 2021-11-16 | 7 | 0%
3.2 | KPIs | Ding | 2021-11-11 | 2021-11-17 | 6 | 0%
3.2.1 | Monitoring | Krishnar | 2021-11-11 | 2021-11-18 | 7 | 0%
3.2.2 | Forecasts | Yoong | 2021-11-13 | 2021-11-20 | 7 | 0%
3.3 | Project Updates | Krishnar | 2021-11-15 | 2021-11-22 | 7 | 0%
3.3.1 | Chart Updates | Ding | 2021-11-15 | 2021-11-23 | 8 | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Ding | 2021-11-20 | 2021-11-25 | 5 | 0%
4.2 | Quality Deliverables | Krishnar | 2021-11-22 | 2021-11-27 | 5 | 0%
4.3 | Effort & Cost Tracking | Yoong | 2021-11-25 | 2021-12-01 | 6 | 0%
4.4 | Project Performance | Krishnar | 2021-12-01 | 2021-12-07 | 6 | 0%
5 | Project Closure
5.1 | Installation | Yoong | 2021-12-08 | 2021-12-10 | 2 | 0%
5.2 | Develop Support Plan | Ding | 2021-12-11 | 2021-12-20 | 9 | 0%
5.3 | System Maintenance | Krishnar | 2021-12-12 | 2021-12-21 | 9 | 0%